## Task list
| Project Name | <insert project name here>
| Current Task Statuses | Not Started | In Progress | Complete | Overdue
|  | 36.36% | 18.18% | 36.36% | 9.091%
|  | Budget | -19.74
|  | Planned | Actual
|  | 1078.26 | 1098
Tasks | Assigned To | Start | End | Days | Status | Planned Cost | Actual Cost | Notes
Choose Event Time | Stacy Williams | 2021-02-01 | 2021-02-01 | 0 | Complete
Create Guest List | Bozo the Clown | 2021-02-02 | 2021-02-03 | 1 | Complete
Create Invitations | Stacy Williams | 2021-02-03 | 2021-02-07 | 4 | Overdue | 10
Purchase Invitation Gift | Jenny Smith | 2016-02-04 | 2016-02-10 | 6 | In Progress | 250.26 | 300
Send Invitations | Stacy Williams | 2021-02-11 | 2021-02-14 | 3 | Not Started | 10 | 8
Hire Event Coordinator | Bozo the Clown | 2016-02-03 | 2016-02-14 | 11 | Complete | 250 | 200
Plan Event Details | Bozo the Clown | 2016-02-03 | 2016-02-21 | 18 | In Progress
Purchase Required Items | Jenny Smith | 2016-02-21 | 2016-02-28 | 7 | Not started | 258 | 280
Lock in Guest List | Stacy Williams | 2016-03-01 | 2016-03-01 | 0 | Not started
Finalize other Hires | Bozo the Clown | 2016-02-03 | 2016-02-28 | 25 | Complete | 300 | 310
Send Reminders | Stacy Williams | 2016-03-07 | 2016-03-10 | 3 | Not started
PARTY! | Everyone

## Reports (hidden)
|  | Workload | Column Labels | [5 empty] | Days | (All)
|  | Row Labels | Complete | In Progress | Not Started | Overdue | (blank) | Grand Total
|  | Everyone |  |  |  |  | 1 | 1 |  | Column Labels
|  | Jenny Smith |  | 1 | 1 |  |  | 2 |  | Create Guest List | Create Invitations | Finalize other Hires | Hire Event Coordinator | Plan Event Details | Purchase Invitation Gift | Purchase Required Items | Send Invitations | Send Reminders | Grand Total
|  | Stacy Williams | 1 |  | 3 | 1 |  | 5 | Sum of Days | 1 | 4 | 25 | 11 | 18 | 6 | 7 | 3 | 3 | 78
|  | Bozo the Clown | 3 | 1 |  |  |  | 4
|  | Grand Total | 4 | 2 | 4 | 1 | 1 | 12
Row Labels | Count of Tasks
Complete | 4
In Progress | 2
Not Started | 4
Overdue | 1
Grand Total | 11
Actual Cost | (All)
Row Labels | Actual
Choose Event Time
Create Guest List
Create Invitations
Finalize other Hires | 310
Hire Event Coordinator | 200
Lock in Guest List
PARTY!
Plan Event Details
Purchase Invitation Gift | 300
Purchase Required Items | 280
Send Invitations | 8
Send Reminders
(blank)
Grand Total | 1098

## How to use this template
How to use this template:
ProjectManager.com has created this Excel template to help you generate easy reports with simple-to-update task lists,
budget tracker, workload view and progress tracker in one!
Simply click into the cells you'd like to change to update the data, and the formulas take care of the rest.
Be sure to click the "Update Reports" button on the Reporting tab to re-populate the reports with the changes you've made.
Finally, you should make sure you have "macros enabled" so that the formulas can work properly.
You can find more templates in our Resources section online.
And, of course, if you can update this Excel template, you can manage projects online, too!
Click here to start your free trial at ProjectManager.com: